## Sheet1
SI No | Submitted Date | Description | Detected Sprint | Module | Component | Severity | Status | Remarks
1 | 2025-12-12 | Emails with HTML tags not cleaned properly during preprocessing | Sprint 1 | Data Preprocessing | NLP Cleaning | Medium | Completed | HTML parser added and verified
2 | 2025-12-12 | Stopwords removal affecting important urgency keywords | Sprint 1 | Preprocessing | Text Normalization | High | Completed | Customized stopword list implemented
3 | 2025-12-23 | Misclassification between complaints and requests | Sprint 2 | Email Categorization | ML Model | High | Completed | BERT fine-tuning improved accuracy
4 | 2025-12-23 | Spam emails classified as feedback | Sprint 2 | Email Categorization | Model Training | Medium | Completed | Added spam-specific features
5 | 2026-01-06 | Urgent emails not marked as high priority | Sprint 3 | Urgency Detection | Rule Engine | High | Completed | Keyword + ML hybrid logic added
6 | 2026-01-06 | False positives in urgency detection | Sprint 3 | Urgency Detection | Model Evaluation | Medium | Completed | Threshold tuning performed
7 | 2026-01-20 | Dashboard not updating email count in real time | Sprint 4 | Dashboard | Frontend | Medium | Completed | WebSocket refresh enabled
8 | 2026-01-20 | Filter by urgency not working correctly | Sprint 4 | Dashboard | UI Filters | Low | Completed | Filter logic fixed
9 | 2026-01-20 | API latency during bulk email classification | Sprint 4 | Deployment | API Performance | High | Completed | Async processing implemented
10 | 2026-01-20 | Cloud deployment configuration error | Sprint 4 | Deployment | Cloud Setup | Medium | Completed | Environment variables corrected